## Sheet1
No. | Action Item | Feasible Y / N | Efforts | Comp Date | Remark
1 | How long to integrate into current process rather than stand alone new "lead entity" - LTI (Discuss |  | 25 days | 2019-04-30 | Dependent on Mahesh, Post today's meeting w'll be able to the Feasibilty and impact Interdependent on 1 and 2
2 | New button on current lead process to open PROS - LTI |  | 5 days | 2019-04-12 | Get details from Erwan in 3'o Clock, Quickly adding through the cart while, already cart build, Interdependent on 1 and 2
3 | New button will jump directly into PROS product selection screen - LTI |  | 2 days | 2019-04-11 | Erwan(Pros) to confirm
4 | Remove Quote grey bar when in PROS - LTI/PROS | Yes | 2 days | 2019-04-05 | Completed
5 | CAn you delete existing quote document when a new proposal is sent back - LTI | Yes | 2 days | 2019-04-10 | Doable
6 | Change "send email" button to "Send Proposal" - LTI | Yes | 1 day | 2019-04-10 | Doable
7 | "Send Proposal" opens webpage : www.steer73.com/?quote=******* - LTI | Yes | 1 day | 2019-04-10 | Doable